## Sheet1
AI project logbook
Phase | Task | Planned start date | Planned end date | Planned duration (hours,minutes) | Actual start date | Actual end date | Actual duration(hours,minutes) | Who is responsible | Notes/Remarks
Preparing for the project | Course,reading | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
| Set up a team folder on a shared drive | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
Defining the | Background reading | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
problem | Research issues in our community | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
| Team meeting to discuss issues and Team meeting to discuss issues and select an issue for theproject | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
| Complete section 3 of the Project Logbook | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
| Rate yourselves | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
Understanding the users | Identify users | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
| Meeting with users to observe them | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
| Interview with user (1) | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
| Interview with user (2), etc… | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
| Complete section 4 of the Project Logbook | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
| Rate yourselves | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
Brainstorming | Team meeting to generate ideas for a solution | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
| Complete section 5 of the Project Logbook | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
| Rate yourselves | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
Designing your solution | Team meeting to design the solution | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
| Complete section 6 of the logbook | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs | Sudhanshu
| Rate yourselves | 2023-05-23 | 2023-05-23 | 1hrs | 2023-05-23 | 2023-05-23 | 1hrs
Collecting and preparing data | Team meeting to discuss data requirements | 2023-05-16 | 2023-05-16 | 1hrs | 2023-05-16 | 2023-05-16 | 1hrs | Sudhanshu
Collecting and preparing data Prototyping | Data collection | 2023-05-16 | 2023-05-16 | 1hrs | 2023-05-16 | 2023-05-16 | 1hrs | Sudhanshu
| Data preparation and labelling | 2023-05-16 | 2023-05-16 | 1hrs | 2023-05-16 | 2023-05-16 | 1hrs | Sudhanshu
| Complete Section 6 of the Project Logbook | 2023-05-16 | 2023-05-16 | 1hrs | 2023-05-16 | 2023-05-16 | 1hrs | Sudhanshu
| Team meeting to plan prototyping phase | 2023-05-16 | 2023-05-16 | 1hrs | 2023-05-16 | 2023-05-16 | 1hrs | Sudhanshu
Prototyping Testing | Train your model with input dataset | 2023-05-17 | 2023-05-17 | 1hrs | 2023-05-17 | 2023-05-17 | 1hrs | Sudhanshu
| Test your model and keep training with more data until you think your model is accurate | 2023-05-17 | 2023-05-16 | 1hrs | 2023-05-17 | 2023-05-17 | 1hrs | Sudhanshu
| Write a program to initiate actions based on the result of your model | 2023-05-17 | 2023-05-16 | 1hrs | 2023-05-17 | 2023-05-17 | 1hrs | Sudhanshu
| Complete section 8 of the Project Logbook | 2023-05-17 | 2023-05-16 | 1hrs | 2023-05-17 | 2023-05-17 | 1hrs | Sudhanshu
| Rate yourselves | 2023-05-17 | 2023-05-16 | 1hrs | 2023-05-17 | 2023-05-17 | 1hrs | Sudhanshu
Team meeting to discuss testing plan
Testing Creating the video | Invite users to test your prototype
Conduct testing with users
Complete section 9 of the Project Logbook
Rate yourselves
Team meeting to discuss video creation
Write your script
Film your video
Edit your video
Completing the logbook | Reflect on the project with your team
Complete sections 10 and 11 of the Project Logbook
Review your Project logbook and video
Submission | Submit your entries on the IBM